## Sheet1
S No. | Date | Milestones
1 | 28 Sep - 4 Oct 2020 | Project Kick off (in the first week) Business problem understanding + QnAs Understanding data - data dictionary, data structure, business rules + QnAs Draft approach formulation and discussion (For unstructured data analysis - Data Collection Pipeline (scraping) if project requires so
2 | 5 Oct - 18 Oct 2020 | Approach Finalization Data sanity checks + preparing data quality report Analytical Dataset preparation - data cleaning, missing value and outlier treatment, feature engineering, if needed Univariate data analysis and report findings (For unstructured data analysis- Data Collection Pipeline (scraping) if project requires so/ image preprocessing
3 | 19 Oct - 1 Nov 2020 | Continue univariate analysis and report findings EDA's and deep dives -Bivariate analysis and findings -Hypothesis testing and results -Insight generation (For unstructured data analysis - cleaning and normalizing of text data to continue)/ image pre processing
VIVA 1 | Between 2 Nov to 8 Nov | Mid term project VIVA for individuals
4 | 2 Nov - 8 Nov 2020 | EDA phase continue. Finalize all EDA results and document them Insight generation and story building Start working on the presentation/ deck - have a high level story flow ready Start Work on the BI tool (if part of the project)
5 | 9 Nov - 22 Nov 2020 | Model building and validation (if applicable for a project) Continue to work on the presentation - build on top of the story flow, make iterations Continue working on the BI tool (if part of the project)
6 | 23 Nov - 6 Dec 2020 | Model finalization Initial draft of Presentation / BI tool to be ready and to be reviewed by the mentor and provide feedback for any changes/ additions
7 | 07 Dec - 20 Dec 2020 | Final presentation/ BI tool to be ready and submitted by end of day (20 Dec). Python/ R code (properly commented) also to be submitted. An internal review to happen with the mentor within these weeks to finalize presentation Final individual Viva Preprations
8 | 21 Dec - 27 Dec 2020 | Buffer
9 | Between 21 Dec to 30 Dec 2020 | Final project VIVA for individuals
10 | 9 Jan 2020 | Online Project presentations
Note-
These timelines/ milestones are tentative and based on project needs can be updated
This plan also include 1 week of buffer time to incorporate any unexpected scenarios